## Software Dev Gantt Chart
Project Development Plan
Project Name:
Task Name | Start (Date) | End (Date) | Actual Days | Estimated Days | On time | Task Status | Priority | Percentage of Completion | Dependencies | Comments | Assigned To
Project requirements | 2025-01-04 | 2025-01-10 | 6 | 4 | -2 | Completed | High | 100
Define scope | 2025-01-11 | 2025-01-19 | 8 | 8 | 0 | Completed | High | 100
Risk management plan | 2025-01-21 | 2025-02-10 | 20 | 20 | 0 | Completed | Medium | 100
UI prototypes | 2025-02-12 | 2025-02-20 | 8 | 8 | 0 | Completed | Medium | 100
Technical architecture | 2025-02-21 | 2025-03-05 | 12 | 10 | -2 | Completed | High | 100
Design approval | 2025-03-06 | 2025-03-15 | 9 | 8 | -1 | Completed | Medium | 100
Development environment | 2025-03-16 | 2025-03-30 | 14 | 13 | -1 | Completed | High | 33
Front-end development | 2025-04-01 | 2025-04-25 | 24 | 20 | -4 | Completed | High | 15
Back-end development | 2025-04-26 | 2025-05-25 | 29 | 35 | 6 | Completed | High | 70
Database setup | 2025-06-01 | 2025-06-15 | 14 | 14 | 0 | Completed | Medium | 60
API development | 2025-06-16 | 2025-06-30 | 14 | 14 | 0 | Completed | Medium | 50
Unit testing | 2025-07-02 | 2025-07-30 | 28 | 28 | 0 | Completed | Medium | 12
User acceptance test | 2025-08-01 | 2025-08-15 | 14 | 14 | 0 | Completed | High | 30
Bug fixes | 2025-08-16 | 2025-08-30 | 14 | 10 | -4 | Completed | High | 100
Deployment environment | 2025-09-01 | 2025-09-15 | 14 | 19 | 5 | Completed | High | 100
Go-live and release | 2025-09-16 | 2025-10-10 | 24 | 24 | 0 | Completed | High | 100
Performance tracking | 2025-10-11 | 2025-10-31 | 20 | 20 | 0 | Completed | Medium | 100
Final project review | 2025-11-02 | 2025-11-08 | 6 | 6 | 0 | Completed | Medium | 100
Project Start Date | 2025-01-04
Project End Date | 2025-11-08
Total Planned Days | 275
Actual Days | 278
Days Balance | -3